## All Tasks
Phase | ID | Title | Description | Predecessors | Complexity | Story/Task Points | Assignee | Status | Comments
0 | T0-01 | Define MVP Scope | Identify core ATROP protocol components to include in the first working version (FSM, AI engine, ML inference, IPC, test tools) | None | Medium | 5 | Protocol Architect | ✅ Done
0 | T0-02 | Draft Product Backlog | Create full Epic/Story breakdown for all core modules: control plane, data plane, SDK, testing, integration | T0-01 | High | 8 | Product Owner + Lead Developer | ✅ Done
0 | T0-03 | Select Agile Workflow | Choose methodology (Scrum/Kanban hybrid), set sprint cadence, grooming cadence, stand-up schedule | None | Low | 2 | Scrum Master | ✅ Done
0 | T0-04 | Setup GitHub Repo Structure | Initialize repo directories per spec (`daemon/`, `test/`, `sdk/`, etc.) with `README.md` stubs | None | Medium | 3 | DevOps Engineer | ✅ Done
0 | T0-05 | Create GitHub Project Board | Set up columns (Backlog, To-Do, In Progress, Review, Done), define issue templates, and configure project automation | T0-04 | Medium | 3 | Scrum Master | ✅ Done
0 | T0-06 | Review Governance Files | Finalize `LICENSE`, `CODE_OF_CONDUCT.md`, `CONTRIBUTING.md`, and `SECURITY.md` | T0-04 | Low | 2 | Legal Advisor + Community Manager | ✅ Done
0 | T0-07 | Define Test Strategy (MVP) | Identify what testing is required at each layer: unit, FSM simulation, integration, telemetry validation | T0-01 | High | 5 | Test Architect | ✅ Done | ✅ Test strategy defined across Phase 6 and 7 tasks
0 | T0-08 | Align Roadmap Milestones | Lock sprint roadmap based on draft index (AI/ML engine, protocol FSM, vendor adapters) | T0-02 | Medium | 3 | Project Manager | ✅ Done | ✅ Roadmap aligned and sprint breakdown defined from Phase 1–7
0 | T0-09 | Assign SMEs to Tracks | Identify domain leads: protocol logic, AI, ML, platform integration, SDK, telemetry | T0-02 | Low | 2 | Tech Lead | ✅ Done | ✅ SMEs assigned in backlog with domain-specific roles
0 | T0-10 | Create Initial Dev Docs | Add intro pages for `docs/` (architecture, diagrams, whitepaper, standards alignment) | T0-01, T0-06 | Medium | 3 | Documentation SME | ✅ Done | ✅ Initial dev docs structure present in `docs/` with README.md
0 | T0-11 | CI Pipeline Bootstrap | Set up `.github/workflows/ci.yml` to run lint + placeholder test stage | T0-04 | Medium | 3 | DevOps Engineer | ✅ Done | 🟡 CI pipeline YAML exists; awaiting validation of test execution (see T1-10)
1 | T1-01 | Scaffold Build System | Create Makefile or setup.py, support for daemon/, sdk/, test/ builds | Phase 0 | Medium | 3 | DevOps | ✅ Done | ✅ Entry build paths for daemon/control_plane, ipc, and data_plane verified with manual test (g++, python)
1 | T1-02 | Initialize Module Entrypoints | Add empty/stub main.cpp, main.py in control_plane, data_plane, ipc | Phase 0 | Medium | 2 | Core Developer | ✅ Done
1 | T1-03 | Finalize Directory Structure | Create placeholder folders and .keep or README.md in all code areas | T1-02 | Low | 1 | Repo Maintainer | ✅ Done | ✅ Directory structure validated, aligned with SWP and committed.
1 | T1-04 | Setup Testing Scaffold | Add pytest for Python, gtest for C++, folder layout under test/ | T1-01 | Medium | 3 | Test Engineer | ✅ Done
1 | T1-05 | Create Local Dev Environment | Dockerfile + .devcontainer/, install deps, shared bash aliases, common tools | T1-01 | Medium | 5 | DevOps | ✅ Done
1 | T1-06 | Extend CI Pipeline | Add testing & lint stages to .github/workflows/ci.yml for Python + C++ | T1-04 | Medium | 3 | DevOps | ✅ Done
1 | T1-07 | Central Config Loader | Add JSON/YAML config parser in daemon, shared across modules | T1-02 | Medium | 5 | Infra Engineer | ✅ Done
1 | T1-08 | Logging Abstraction | Create unified logger (file, console, JSON) for daemon + test use | T1-07 | Medium | 3 | Infra Engineer | ✅ Done
1 | T1-09 | Add Placeholder Protocol Handlers | Create empty message parsing stubs for Discovery/Decision/Observation packets | T1-02 | Medium | 3 | Protocol Engineer | ✅ Done
1 | T1-10 | Add Dummy Unit Test | One passing test per module to validate test infra (CI smoke test) | T1-04 | Low | 1 | Test Engineer | ✅ Done
2 | T2-01 | Define Core ATROP States | Implement INIT, DISCOVERY, LEARN, DECIDE, ENFORCE, OBSERVE, FEEDBACK, CORRECT, EXIT | T1-02 | High | 8 | Protocol Architect | 🔵 To Do
2 | T2-02 | Implement FSM Transitions | Encode FSM transitions (event-driven) in state engine | T2-01 | High | 5 | Protocol Engineer | 🔵 To Do
2 | T2-03 | Create Packet Parser & Dispatcher | Handle ATROP message families: Discovery, Decision, Correction, etc. | T1-09 | Medium | 5 | Core Dev | 🔵 To Do
2 | T2-04 | Parse Protocol Headers | Decode NIV, PIV, IDR, FIF in incoming packets (binary or TLV) | T2-03 | Medium | 3 | Protocol Dev | 🔵 To Do
2 | T2-05 | Implement ATZ Zone Formation | Create zone map, assign zone ID, handle zone-based FSM logic | T2-01 | High | 5 | Topology Dev | 🔵 To Do
2 | T2-06 | Embed Policy Awareness Hooks | Integrate policy checks into FSM before transitions (e.g., intent match) | T2-02 | Medium | 3 | Policy/Intent Dev | 🔵 To Do
2 | T2-07 | Add Correction Packet Handler | Handle anomaly feedback & trigger FSM fallback (CORRECT → ISOLATE) | T2-01, T2-02 | Medium | 3 | Protocol Dev | 🔵 To Do
2 | T2-08 | Build FSM Unit Test Suite | Test state transitions, valid/invalid events, stub simulation | T2-01 | Medium | 3 | Test Engineer | 🔵 To Do
2 | T2-09 | Simulate ATZ Formation + Split | Add test scenario: node joins, forms zone, then splits due to anomaly | T2-05 | Medium | 3 | Test/Sim Engineer | 🔵 To Do
2 | T2-10 | Document Protocol Flow | Sequence diagrams: packet in → FSM → response → state update | All | Low | 2 | Documentation SME | 🔵 To Do
3 | T3-01 | Build AI Model Engine | Implement core control-plane model using GNN or RL (basic route inference) | T2-01, T2-02 | High | 8 | AI Engineer | 🔵 To Do
3 | T3-02 | Topology Analytics Engine | Build module to maintain graph of real-time ATZ state (nodes, metrics, links) | T2-05 | Medium | 5 | AI/Graph Dev | 🔵 To Do
3 | T3-03 | Intent Processing Unit (IPU) | Translate user/service intents into policies (SLA, path constraints, zones) | T2-06 | Medium | 3 | Intent Architect | 🔵 To Do
3 | T3-04 | Feedback Loop Receiver | Parse telemetry (PIV, FIF) from ML data plane to guide model updates | T2-08 | Medium | 3 | Feedback Engineer | 🔵 To Do
3 | T3-05 | Decision Policy Orchestrator | Validate AI outputs, apply policy, trust scores, and inject final route decisions | T3-01, T3-03 | High | 5 | Protocol/AI Lead | 🔵 To Do
3 | T3-06 | Model Confidence + Fallback | Integrate confidence scoring, rollback logic, and safe-mode policy fallback | T3-01 | Medium | 3 | AI Safety Engineer | 🔵 To Do
3 | T3-07 | Unit Tests for AI Components | Add tests for AI inference, intent mapping, feedback processing | T3-01, T3-04 | Medium | 3 | Test Engineer | 🔵 To Do
3 | T3-08 | Federated Training Mock | Simulate per-ATZ model learning, sync gradients to a mock controller | T3-01 | Medium | 3 | AI Researcher | 🔵 To Do
3 | T3-09 | Policy-Driven Routing Simulation | Simulate AI-based decision under different intents (video, bulk, secure) | T3-05, T3-03 | Medium | 3 | AI/Test Engineer | 🔵 To Do
3 | T3-10 | Document AI Routing Flow | Diagram: topology change → feedback → AI model → routing decision → inject | T3-01, T3-05 | Low | 2 | Documentation SME | 🔵 To Do
4 | T4-01 | ML Inference Agent | Build daemon to classify flows in real-time using lightweight model (e.g., DT, CNN) | T3-01 | High | 8 | ML Engineer | 🔵 To Do
4 | T4-02 | Flow Classification Model | Implement or fine-tune basic model (app type, congestion, latency pattern) | T4-01 | Medium | 5 | Data Scientist | 🔵 To Do
4 | T4-03 | Flow Trust Score Engine | Assign dynamic trust values per link/flow for security-aware forwarding | T4-02 | Medium | 5 | ML Engineer | 🔵 To Do
4 | T4-04 | Feedback Injection Generator | Create FIF telemetry packets from data-plane observations | T4-01 | Medium | 4 | Telemetry Dev | 🔵 To Do
4 | T4-05 | Model Loader API | Allow loading and hot-swapping of new model versions at runtime | T4-01 | Medium | 3 | Infra Dev | 🔵 To Do
4 | T4-06 | Safety Fallback Hooks | Allow bypass of inference when CPU/memory budget exceeded or confidence low | T4-01 | Medium | 3 | Safety Engineer | 🔵 To Do
4 | T4-07 | Inline Flow Tap Hook | Connect ATROP ML with Linux Netfilter/IPTables or eBPF hooks for per-packet visibility | T4-01 | High | 5 | Platform Dev | 🔵 To Do
4 | T4-08 | Flow Behavior Simulation | Simulate various flows (video, bulk, bursty) and observe ML response + FIF output | T4-01, T4-02 | Medium | 4 | Test Engineer | 🔵 To Do
4 | T4-09 | Unit Tests (Inference Path) | Tests for flow vectorization, model call, FIF telemetry construction | T4-01 | Medium | 3 | Test Engineer | 🔵 To Do
4 | T4-10 | Integration Test with Control Plane | Ensure control plane reacts to FIF (feedback to AI engine) | T4-04, T3-04 | High | 5 | Integration Lead | 🔵 To Do
4 | T4-11 | Brownfield Shadow Mode | Add mode for passive ML inference (non-enforcing) for legacy deployments | T4-01 | Medium | 3 | Compatibility Dev | 🔵 To Do
4 | T4-12 | Document ML Path & FIF | Sequence: packet → model → trust → FIF → AI feedback | T4-01, T4-04 | Low | 2 | Documentation SME | 🔵 To Do
5 | T5-01 | Define IPC Protocol Spec | Establish message types, headers, and format (e.g., protobuf, JSON) | Phase 0 | Medium | 3 | Protocol Engineer | 🔵 To Do
5 | T5-02 | Build IPC Server (Daemon Hub) | Create central IPC hub (UNIX domain sockets or gRPC-based) | T5-01 | High | 5 | Infra Dev | 🔵 To Do
5 | T5-03 | Create IPC Clients | Add client libraries for control plane, data plane, model agent | T5-02 | High | 5 | Core Dev | 🔵 To Do
5 | T5-04 | Shared Memory or Queue System | Add FIF/decision queue for async messaging (e.g., multiprocessing.Queue, ring buffers) | T5-01 | High | 5 | Systems Engineer | 🔵 To Do
5 | T5-05 | Define Agent Lifecycle Protocol | Support agent registration, capabilities, version negotiation | T5-02 | Medium | 3 | Infra/Platform Lead | 🔵 To Do
5 | T5-06 | Reloadable Config Handling | IPC messages to trigger runtime reload of models, policies, params | T5-02 | Medium | 3 | Infra Dev | 🔵 To Do
5 | T5-07 | IPC Security Layer | Add authentication, socket permission enforcement, agent identity | T5-01 | High | 5 | Security Engineer | 🔵 To Do
5 | T5-08 | Unit Tests for IPC Protocol | Test all message types, malformed input, reconnects | T5-01, T5-03 | Medium | 3 | Test Engineer | 🔵 To Do
5 | T5-09 | IPC Integration Testbed | Full test across live agents exchanging FIF, model updates, commands | T5-04, T5-06 | High | 4 | Integration Engineer | 🔵 To Do
5 | T5-10 | Daemon Identity and Uptime Tracker | Each agent maintains state, heartbeat, and logs version + start time | T5-05 | Medium | 3 | Core Engineer | 🔵 To Do
5 | T5-11 | Document IPC Interface & Messages | Message catalog, sequence examples, security requirements | T5-01 to T5-03 | Low | 2 | Documentation SME | 🔵 To Do
6 | T6-01 | Setup Python Unit Test Infra | Use pytest, folder structure, test discovery, config | T1-04 | Medium | 3 | Test Engineer | 🔵 To Do
6 | T6-02 | Setup C++ Unit Test Infra | Use gtest + CMake test targets in daemon modules | T1-04 | Medium | 4 | C++ Dev/Test | 🔵 To Do
6 | T6-03 | Organize Unit Test Layout | Per-module folder: ai_control_plane, ml_data_plane, protocol, ipc, fsm | T1-04 | Medium | 2 | QA Lead | 🔵 To Do
6 | T6-04 | Write Protocol Parsing Tests | Unit tests for header parsing (NIV, PIV, IDR, FIF) | T2-04 | Medium | 3 | Protocol Dev | 🔵 To Do
6 | T6-05 | Write FSM Transition Tests | Test valid and invalid state transitions and triggers | T2-02 | Medium | 3 | Protocol Dev | 🔵 To Do
6 | T6-06 | Write ML Inference Tests | Validate flow vectorization, classification, FIF emission | T4-01 | Medium | 3 | ML Dev | 🔵 To Do
6 | T6-07 | Write AI Decision Tests | Check AI engine outputs match expected intent/policy routes | T3-01 | Medium | 3 | AI Dev | 🔵 To Do
6 | T6-08 | Write IPC Protocol Tests | Test encoding/decoding of IPC messages, connection handling | T5-03 | Medium | 3 | Test Engineer | 🔵 To Do
6 | T6-09 | CI: Auto Trigger Unit Tests | Run all tests via GitHub Actions (ci.yml) on push/PR | T1-11 | Medium | 3 | DevOps | 🔵 To Do
6 | T6-10 | Test Reporting Setup | Output results in HTML, JSON for coverage and visibility | T6-01, T6-02 | Medium | 2 | QA Lead | 🔵 To Do
6 | T6-11 | Regression Test Baseline | Freeze and validate known-good tests (per release/sprint) | T6-01 to T6-08 | Medium | 2 | QA Lead | 🔵 To Do
6 | T6-12 | Document Testing Strategy | How to write, run, extend, and interpret unit tests | All above | Low | 2 | Documentation SME | 🔵 To Do
7 | T7-01 | Integration Test Framework | Setup testing harness for Mininet, FRRouting, or containerized ATZ | T1-04 | High | 5 | Integration Lead | 🔵 To Do
7 | T7-02 | AI + ML Feedback Integration Test | Simulate flow → FIF → AI policy adjustment → route decision | T3-04, T4-04 | High | 5 | AI/ML Dev | 🔵 To Do
7 | T7-03 | Intent-Based Routing Validation | Send intent policy, validate correct path enforced across ATZ nodes | T3-03, T3-05 | Medium | 4 | Policy Tester | 🔵 To Do
7 | T7-04 | Topology Change Response Test | Simulate node/link failures, ensure AI re-learns topology and updates path | T3-02, T2-01 | Medium | 4 | Topology Engineer | 🔵 To Do
7 | T7-05 | Flow Behavior Sensitivity Test | Test ML reaction to bursty, video, or malicious flows with label output | T4-02, T4-08 | Medium | 3 | Data Plane QA | 🔵 To Do
7 | T7-06 | Multi-Zone FSM Sync Test | Ensure FSMs in multiple zones respond to cross-ATZ corrections | T2-01, T2-05 | Medium | 3 | Protocol Engineer | 🔵 To Do
7 | T7-07 | Legacy Protocol Integration Test | Connect ATROP testbed with FRR (OSPF/BGP), validate interop | T1-04, Phase 0 | Medium | 4 | FRR Integration Lead | 🔵 To Do
7 | T7-08 | Packet Capture & Verification | Collect real traffic and compare packet headers (PIV, IDR, etc.) | T2-04, T4-04 | Medium | 3 | Packet Analyst | 🔵 To Do
7 | T7-09 | Integration Regression Test Set | Define & freeze integration test scenarios for reuse in CI | T7-01 to T7-07 | Medium | 3 | QA Lead | 🔵 To Do
7 | T7-10 | Document Integration Scenarios | Describe topology diagrams, intent policies, flow types, expected results | T7-01 to T7-05 | Low | 2 | Documentation SME | 🔵 To Do
8 | T8-01 | Build Emulated Testbed | Create emulated lab using Mininet, Docker or container topology tools | T7-01 | High | 5 | Platform Engineer | 🔵 To Do
8 | T8-02 | Design Topology Scenarios | Simulate DC spine-leaf, 5G edge, WAN backbone, metro ring | T8-01 | High | 5 | Testbed Architect | 🔵 To Do
8 | T8-03 | Automate Simulation Scripts | Use YAML/JSON-driven topology configs and scripts | T8-01 | Medium | 3 | Testbed DevOps | 🔵 To Do
8 | T8-04 | Simulate ATZ Split/Merge | Inject zone failures, convergence changes, observe FSM reactions | T2-05, T7-06 | Medium | 4 | Protocol Engineer | 🔵 To Do
8 | T8-05 | Churn + Failure Injection | Simulate link/node flaps, blackholes, prefix hijacks, CPU load | T4-04, T6-06 | Medium | 4 | Simulation Engineer | 🔵 To Do
8 | T8-06 | Legacy Redistrib. Validation | Validate BGP/OSPF/MPLS/Segment Routing interop under ATROP | T7-07 | High | 4 | Legacy Interop SME | 🔵 To Do
8 | T8-07 | Flow Replay Testing | Replay known PCAPs (e.g., video, attack traffic) and observe ML response | T4-08, T6-06 | Medium | 3 | ML QA | 🔵 To Do
8 | T8-08 | Capture Metrics & Logs | Collect convergence time, path change rates, AI vs static routes | T3-05, T7-09 | Medium | 3 | Observability Engineer | 🔵 To Do
8 | T8-09 | Pre-Production Staging Run | Full stack test in emulated staging zone, with fallback protocols | All | High | 5 | Systems QA Lead | 🔵 To Do
8 | T8-10 | Document Simulation Framework | Detail all testbed scenarios, toolchains, metrics, PCAPs used | T8-01 to T8-09 | Low | 2 | Documentation SME | 🔵 To Do
9 | T9-01 | Define API Contract | Define all API endpoints: /inject, /telemetry, /models, /zones etc. | Phase 0 | Medium | 3 | API Architect | 🔵 To Do
9 | T9-02 | Python SDK Core | Implement SDK client with auth, CLI tools, REST/gRPC calls | T9-01 | Medium | 4 | Python Dev | 🔵 To Do
9 | T9-03 | gRPC API Definition | Create .proto files for real-time telemetry + policy injection | T9-01 | Medium | 4 | gRPC Engineer | 🔵 To Do
9 | T9-04 | C++ SDK Stubs | Provide C++ wrappers for embedded systems (Edge nodes) | T9-01 | Medium | 3 | C++ Dev | 🔵 To Do
9 | T9-05 | Telemetry API Implementation | Export path decisions, ATZ trust, state logs via API | T3-05, T4-04 | Medium | 3 | Protocol Dev | 🔵 To Do
9 | T9-06 | Model Upload Endpoint | Allow pushing updated AI/ML models into control/data planes | T3-01, T4-01 | Medium | 3 | ML Platform Dev | 🔵 To Do
9 | T9-07 | YANG Model Generation | Define ATROP control/telemetry in YANG (RFC 6020+) | T9-01 | Medium | 3 | NETCONF Engineer | 🔵 To Do
9 | T9-08 | Secure API Layer | Enforce role-based access, API tokens, certificate auth | T9-01 | Medium | 4 | Security Engineer | 🔵 To Do
9 | T9-09 | Unit Tests for SDK | Validate all client methods, schemas, and error handling | T9-02 to T9-04 | Medium | 3 | SDK QA | 🔵 To Do
9 | T9-10 | Vendor Hook Integration | Implement sample integrations (e.g., JunOS hook, IOS-XR parser) | T9-01 | High | 4 | Vendor Integration Lead | 🔵 To Do
9 | T9-11 | Document SDK Usage | Code examples, API call examples, integration flows, diagrams | T9-01 to T9-09 | Low | 2 | Documentation SME | 🔵 To Do
10 | T10-01 | Package Agent Stack | Bundle ATROP daemon(s) into DEB/RPM/Container with versioning | T1-01, T5-10 | High | 5 | Release Engineer | 🔵 To Do
10 | T10-02 | Create Systemd Service Files | Provide atrop-agent.service, atrop-ctrl.service, and config templates | T5-10 | Medium | 3 | Platform Dev | 🔵 To Do
10 | T10-03 | Final Golden Topology Validation | Run all test cases on final topology (DC, WAN, MPLS) | T8-09 | High | 5 | QA Lead | 🔵 To Do
10 | T10-04 | Performance Profiling | CPU, memory, inference time, packet latency profiling | T4-01, T3-01 | Medium | 4 | Performance Analyst | 🔵 To Do
10 | T10-05 | Fault Isolation Hooks | Ensure agents isolate, restart, or enter safe mode on crash or overload | T6-06, T5-02 | Medium | 4 | Platform Engineer | 🔵 To Do
10 | T10-06 | License & Security Audit | Validate licensing, run SBOM generator, scan for CVEs | T0-06 | Medium | 3 | Security Lead | 🔵 To Do
10 | T10-07 | Release Candidate Snapshot | Create reproducible version bundle: source, binaries, docs, testcases | All | Medium | 3 | Release Manager | 🔵 To Do
10 | T10-08 | Deployment Runbook | Document steps for install, startup, restart, logging, telemetry export | T10-01 to T10-02 | Low | 2 | Documentation SME | 🔵 To Do
10 | T10-09 | Final Integration with Vendor Hooks | Validate ATROP API or telemetry integration with JunOS, EOS, etc. | T9-10 | High | 4 | Vendor Integration Lead | 🔵 To Do
10 | T10-10 | Sign-off Checklist & Go/No-Go | Formal verification checklist with regression, coverage, security, and vendor criteria | All | Medium | 2 | Project Manager | 🔵 To Do

## Status Key
Emoji | Status | Meaning
🔵 | To Do | Planned but not started
🟡 | In Progress | Currently under active execution
✅ | Done | Task completed and reviewed
🟣 | Review | Awaiting final check/approval
⏳ | Blocked | Blocked by dependency or issue